## ProjectSchedule
Unmanned Ground Vehicle Project
TheBoys | Project Start: | 2023-03-30
| Today: | 2023-04-13
| Display Week: | 1 |  |  | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29 | [6 empty] | 2023-06-05
 | time axis 2023-03-27 to 2023-06-11
TASK | PROGRESS | START | END | DAYS | time axis 2023-03-27 to 2023-06-11
Literature Search
Project Proposal | 100% | 2023-03-27 | 2023-03-30 | 4
Commercial Product Search | 60% | 2023-03-30 | 2023-04-13 | 15
Patent Search | 50% | 2023-04-06 | 2023-04-13 | 8
State of the Art Survey | 60% | 2023-04-07 | 2023-04-13 | 7
Conceptual Design
Problem Definition | 100% | 2023-04-07 | 2023-04-11 | 5
Functional Decomposition | 20% | 2023-04-12 | 2023-04-18 | 7
Brain Storming | 30% | 2023-04-10 | 2023-04-20 | 11
Morphological Chart | 0% | 2023-04-14 | 2023-04-21 | 8
Assesment of Concepts | 0% | 2023-04-17 | 2023-04-25
Preliminary Sketches | 0% | 2023-04-19 | 2023-04-27 | 9
Detailed Design
System Architecture Design | 0% | 2023-04-26 | 2023-05-05 | 10
Hardware Component Selection | 0% | 2023-05-04 | 2023-05-07 | 4
Software Component Selection | 0% | 2023-05-05 | 2023-05-08 | 4
Mechanical Design | 0% | 2023-05-07 | 2023-05-16 | 10
Control System Design | 0% | 2023-05-10 | 2023-05-17
Safety Measures Design | 0% | 2023-05-14 | 2023-05-18
Prototyping | 0% | 2023-05-17 | 2023-05-27
Manufacturing and Testing
Manufacturing | 0% | 2023-05-27 | 2023-05-30 | 4
Assembly | 0% | 2023-05-30 | 2023-05-31 | 2
Testing and Validation | 0% | 2023-05-31 | 2023-06-09 | 10
Refinement and Optimization | 0% | 2023-06-04 | 2023-06-09 | 6
Project Closeout
Finalize Documentation | 0% | 2023-06-09 | 2023-06-10 | 2
Assess Project Success | 0% | 2023-06-10 | 2023-02-11 | -118
Insert new rows ABOVE this one
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.